## Sheet1
ADNOC GAS EPC FOR BALANCE OF PLANT (BOP) WORKS FOR HABSHAN - P5 SHORT TERM FACILITIES PROJECT COMPANY PROJECT No. 30201-50150-ST-HB WORK ORDER NO. 4700025491
Comments Resolution Sheet (CRS)
COMPANY Trans. No.: |  | ADNOCGP-WTRAN-002723 | [5 empty] | Received Date: |  | 2025-04-25
COMPANY Doc. No.: |  | DOD-30201-50150-ST-HB-GG-001-00-00-019 | [5 empty] | Revision: |  | A
Document Title: |  | ENGINEERING EXECUTION PLAN | [5 empty] | Status Code: |  | 2
ADNOC PM: |  | Mr. Ameen Humaidah | [5 empty] | ENGG. CONTRACTOR PM: |  | D. Jeyakumar
ADNOC Reviewer: |  | Mr. Hariprasad Thazhe Punathil | [5 empty] | ENGG. CONTRACTOR Originator: |  | Kareem Ahamed
Review Codes: |  | Code-1: Rejected |  | Code 2: Comments as Noted
|  | Code-3: No Comments |  | Code 4: For Information Only
REVISION A (ADNOCGP-WTRAN-002723)
No. | COMMENT SECTION/ CLAUSE / DRAWING REFERENCE | COMPANY Comment | COMPANY Reviewer | ENGINEERING CONTRACTOR Response | Open/Closed | COMPANY Response (If Comments are still open / Not incorporated or if Eng Contractor Response Not Acceptable) | ENGINEERING CONTRACTOR Response | Open/Closed | Remarks
1 | Page 1 of 36 | As EPC Contractor, all documents shall be signed by RSME team as well. | Sandeep Prabhakar | Noted and Updated | CLOSED
2 | Page 5 of 36 | Pls clarify this is for BOP or H5 or common accordingly update the sections. | Mr Kausik Biswas | It is common for H5 and BOP (Entire Scope) | CLOSED
3 | Page 6 of 36 | BOP and H5 are different scope. Please clarify | Mr Noman Anwar | BOP and H5 are different scope but it is a single project | CLOSED
4 | Page 6 of 36 | Include or clarify why these are not added- Project control procedure, Document control procedure, Project Interface register, Inter discipline checks matrix | Mr Vijayakrishnan Anan | Noted and Updated | CLOSED
5 | Page 7 of 36 | Engineering quality plan | Mr Manjunath Alayil Ve | Noted and Updated | CLOSED
6 | Page 7 of 36 | Include HSE related AGES | Mr Srikanth Ramani | Noted and Updated | CLOSED
7 | Page 8 of 36 | Add All Applicable Exhibits | Mr Manjunath Alayil Veetil | Noted and Updated | CLOSED
8 | Page 8 of 36 | All AGES are applicable, no civil/structural AGES are listed. Kindly update. | Mr Fouad_Yaqub Salik | Noted and Updated | CLOSED
9 | Page 10 of 36 | Include / List all the abbreviations used in this document eg. IDC, LDE | Sandeep Prabhakar | Noted and Updated | CLOSED
10 | Page 11 of 36 | Is there any free issued items for BOP scope? | Mr Kausik Biswas | Not applicable for BOP Scope | CLOSED
11 | Page 11 of 36 | Include site survey inputs | Mr Vijayakrishnan Anantharathina | Noted and Updated | CLOSED
12 | Page 11 of 36 | Telecom to be included. | Mr Kausik Biswas | Noted and Updated | CLOSED
13 | Page 11 of 36 | Critical rating document applicable for this project to be prepared and issued | Mr Kausik Biswas | Noted and Updated | CLOSED
14 | Page 11 of 36 | Include separate section for 1) 3D model development, administartion and management 2) Technical Query, DCAs, Site Technical Queries, Site Change notice, etc 3) Procurement Engineering 4) Vendor Document Review | Sandeep Prabhakar | Noted and Updated | CLOSED
15 | Page 12 of 36 | Contractor shall conduct all the design reviews and workshops required as per SoW. Refer Cl. 14.9.6. Include separate clause of the same in EEP. 1)P&ID Design Review 2) Plot Plan review. 3) PHA (HAZID / ENVID / OHID) 4) HAZOP, 5) SIL 6) Safety Layout Review 7) 30%, 60% & 90% 3D Model review 8) Constructability 9) SIMOPS 10) ISDR 11) Bow-Tie 12) PHASER 13) BAT Workshop | Sandeep Prabhakar | Noted and Updated | CLOSED
16 | Page 12 of 36 | Pls provide the following sections. a) Engineering KPI b) Project Engg. Schedule c) Engg Meeting strategy, (Weekly , with Company etc) d) Engg team location and the scope for each location. e) Software list with versions for each discipline f) Workshops and safety studies planned | Mr Kausik Biswas | Noted and Updated | CLOSED
17 | Page 13 of 36 | Include all the documents required as per Scope of work under respective disciplines. Also, refer PMC comments on PDDR. | Mr Kausik Biswas | Noted and Updated | CLOSED
18 | Page 13 of 36 | Please elobrate updating? Define stage document are only for reference | Sandeep Prabhakar | Noted & updated. | CLOSED
19 | Page 13 of 36 | Unit Plot Plan | Mr Noman Anwar | Noted & updated. | CLOSED
20 | Page 13 of 36 | What is the difference? | Mr Noman Anwar | Noted & updated.There is no difference between tie-in list and schedule. | CLOSED
21 | Page 13 of 36 | Tie-in Key Plan | Mr Sanjay Ramachandran | Noted. Key Plan is not required since loction of tie-in is identified on Unit Plot Plan , Piping GA & piping Isometrics. | CLOSED
22 | Page 14 of 36 | This is construction related document Why it is included in Piping? | Mr Noman Anwar | Noted. Tie-in Package will be the compilation of tie-in related docs & drawings such as Tie-in List/Schedule, related P&IDs, Piping GA, Plot Plan, related Piping Isometrics, MTO and brief Method Statement of performing tie-ins which will be prepared by engineering for construction purpose. | CLOSED
23 | Page 14 of 36 | Critical Line List | Mr Sanjay Ramachandran | Noted & updated. | CLOSED
24 | Page 14 of 36 | Why 2 separate documents???? | Mr Noman Anwar | Noted & updated. | CLOSED
25 | Page 14 of 36 | What about AIV/FIV??? | Mr Noman Anwar | Noted & updated. | CLOSED
26 | Page 14 of 36 | What about 3D Model related documents??? | Mr Noman Anwar | Noted & updated. | CLOSED
27 | Page 14 of 36 | MR for valves????? | Mr Noman Anwar | Noted & updated. | CLOSED
28 | Page 14 of 36 | Pipe Support Standard | Mr Sanjay Ramachandran | Noted & updated. | CLOSED
29 | Page 14 of 36 | Include 30%, 60% and 90% 3D Model Review Reports and Close out reports for each stage separately (total 6 documents) | Sandeep Prabhakar | Noted & updated. | CLOSED
30 | Page 14 of 36 | Add MR & TBE for Structural Steel Supply & Fabrication Also add SOW and TBE for Geotechnical & Topographical Surveys. | Mr Fouad_Yaqub Salik | Noted & updated. | CLOSED
31 | Page 16 of 36 | Mention software list used for all disciplines | Mr Vijayakrishnan Anantharathina | Noted & updated. | CLOSED
32 | Page 16 of 36 | Bulk Items | Mr Pritam Sen | Noted & updated. | CLOSED
33 | Page 16 of 36 | Adequacy reports for UPS, SLD for UPS & PDPs, Space reservation requests in existing Lighting panels and UPS PDPs. | r Vijayakrishnan Anantharathina | Noted & updated. | CLOSED
34 | Page 16 of 36 | Solar panel demolition and relocation drawings, To be included | r Vijayakrishnan Anantharathina | Noted & updated. | CLOSED
35 | Page 16 of 36 | TBE | Mr Pritam Sen | Noted & updated. | CLOSED
36 | Page 16 of 36 | ADD: - Solar Power unit related documentation (as applicable) - Interface / tie-in , Shut-down , Changeover Schedule - Earthing Calculation - Site Visit Report - Modification SOW - IPCS/ ECMS related documentation - Interconnection Schedule - MTO - Substation / Electrical Room related documentation | Mr Pritam Sen | Noted & updated. | CLOSED
37 | Page 17 of 36 | lightning Protection layout | Mr Pritam Sen | Noted and Updated | CLOSED
38 | Page 17 of 36 | Kindly put a note that for list of I&C documents refer PDDL. | Mr Kausik Biswas | Noted and Note added in Secton 6.6 | CLOSED
39 | Page 18 of 36 | Include telecom related deliverables. | Mr Kausik Biswas | Separate Telecom section 6.7 prepared for all telecom deliverables | CLOSED
40 | Page 18 of 36 | Include General document like EQP Add Addendum to AGES | Mr Manjunath Alayil Veetil | EQP is quality related document and shall be included in quality section. As of now there is no deviation found as per AGES | CLOSED
41 | Page 18 of 36 | MDS /PDS / affected Vendor documents ? | Amod Ashokkumar | Noted and Updated | CLOSED
42 | Page 18 of 36 | Include following documents 1) Material Adequacy Check Report 2) Baseline Inspection Survey Procedure and reports 3) Scope of work for Risk Based Inspection (RBI) study 4) Include all other documents required as per Scope for Work including those for Cathodic protection (refer cl. 14.3.8) | Sandeep Prabhakar | Material and Corrosion deliverables are as per section 6.9, Item 1 is included in Material selection report. Item 2, 3 and 4 is Contractor Scope (RSME) | CLOSED
43 | Page 20 of 36 | Include TBE for Safety Studies, MR for Safety signs, HAC layout, PFP layout, PFP schedule. | Mr Srikanth Ramani | Noted & updated. | CLOSED
44 | Page 23 of 36 | This is part of H5 | Mr Kausik Biswas | Noted & updated. | CLOSED
45 | Page 23 of 36 | What is the definition of LLIs? | Mr Noman Anwar | LLI = LONG LEAD ITEMS from Procurement point of view. | CLOSED
46 | Page 23 of 36 | April Shutdown is for H5 Scope not BOP scope. | Mr Noman Anwar | Noted & updated. | CLOSED
47 | Page 24 of 36 | What is teh differences between Sr. No. 3, 4 & 5? | Mr Noman Anwar | Noted & updated. | CLOSED
48 | Page 24 of 36 | Include UPS PDP and integrated as part of YOKOGAWA | Mr Vijayakrishnan Anantharathi | Noted & updated. | CLOSED
49 | Page 24 of 36 | Please elaborate the work share / scope split between EPC Contractor and Engineering Sub-Contractor and the responsibilities of each party | Sandeep Prabhakar | This is engineering execution plan however we have updated the breif scope of EPC contractor and Engineering Subcontractor Responsibility | CLOSED
50 | Page 26 of 36 | Please explain the role and responsibility of EPC Contractor's Engineering Manager and Enginering Sub-Contractor Engineering manager. This is required for all key personnel | Sandeep Prabhakar | Noted & updated. | CLOSED
51 | Page 27 of 36 | Provide the role of the CONTRACTOR and Sub Contractor Leads | Mr Kausik Biswas | Noted & updated. | CLOSED
52 | Page 27 of 36 | Check the Proposal/Approval status -typi | Mr Manjunath Alayil Veetil | Noted & updated. | CLOSED
53 | Page 27 of 36 | He/She-typi | Mr Manjunath Alayil Veetil | Noted & updated. | CLOSED
54 | Page 28 of 36 | DCA? | Mr Manjunath Alayil Veetil | Noted & updated. | CLOSED
55 | Page 28 of 36 | and | Sandeep Prabhakar | Noted & updated. | CLOSED
56 | Page 28 of 36 | Not acceptable. IDC is required Plot plan and P&IDs being critical documents. | Sandeep Prabhakar | Noted & updated. | CLOSED
57 | Page 28 of 36 | Please include and explain the requirement of self-check and discipline check by Lead or nominated checker | Sandeep Prabhakar | Noted & updated. | CLOSED
58 | Page 29 of 36 | As EPC Contractor, all documents shall be signed by RSME team as well. | Sandeep Prabhakar | Noted & updated. | CLOSED
59 | Page 29 of 36 | Time period for EPC review for each rev and Engg Subcon also to be updated | Mr Manjunath Alayil Veetil | Noted and Updated | CLOSED
60 | Page 29 of 36 | Company will provide the comments on the document / drawing itself. EPC Contractor shall compile and prepare the Comment Resolution sheet. | Sandeep Prabhakar | Noted and Updated | CLOSED
61 | Page 30 of 36 | Add procedure no. here… | Mr Fouad_Yaqub Salik | Noted and Updated | CLOSED
62 | Page 31 of 36 | Also add - Weekly Engineering Review meeting: Weekly Engineering Review meeting between EPC Contractor and Company to be held to review the status of engineering and identify the actions required. | Sandeep Prabhakar | Noted and Updated | CLOSED
63 | Page 32 of 36 | SDC/IDC | Mr Manjunath Alayil Veetil | Noted and Updated | CLOSED
64 | Page 32 of 36 | Evidence of review/checking of Avenir documents by RSME engineers shall be maintained and made available if requested by Company engineers. | Mr Fouad_Yaqub Salik | Noted and Updated | CLOSED
65 | Paage 33 of 36 | Workshare / scope matrix between EPC Contractor and Engineering Sub-Contractor for each Discipline shall be prepared and included here. | Sandeep Prabhakar | Noted and Updated | CLOSED
66 | Page 33 of 36 | As EPC Contractor, RSME is responsible for overall Engineering and management | Sandeep Prabhakar | Noted and Updated | CLOSED
67 | Paage 33 of 36 | CONTRACTOR should be responsible | Mr Kausik Biswas | Noted and Updated | CLOSED
68 | Page 33 of 36 | Provide discipline wise work matrix between contractor and sub contractor | Mr Kausik Biswas | Noted and Updated | CLOSED
69 | Paage 33 of 36 | ?? | Sandeep Prabhakar | Noted and Updated | CLOSED
70 | Page 33 of 36 | Include site survey data retrival, base drawing collection include accordinglyInclude site survey data retrival, base drawing collection include accordingly | Mr Vijayakrishnan Anantharat | Noted and Updated | CLOSED
71 | Page 33 of 36 | What is scope split of FAT, Inspection & Testing participation of Engineers and Engg support for Construction & commissioning | Mr Kausik Biswas | Noted and Updated | CLOSED
72 | Page 34 of 36 | Many items are missing in this matrix eg. Material Procurement, Vendor Drawing Review, Site Visits, 3D Modelling, 3D model administration, Engineering documents, etc. | Sandeep Prabhakar | Noted and Updated | CLOSED
73 | Page 35 of 36 | Org Chart for EPC Contractor's Engineering team shall also be provided / included here | Sandeep Prabhakar | Noted and Updated | CLOSED
74 | Page 35 of 36 | Include RSME Discipline Leads in this Org. Chart | Sandeep Prabhakar | Noted and Updated | CLOSED
75 | Page 35 of 36 | Please provide status of mobilization | Mr Vijayakrishnan Anantharathina | Noted and Updated | CLOSED
76 | Page 35 of 36 | Org Chart to be updated indicating Leads approved by Company | Sandeep Prabhakar | Noted and Updated | CLOSED
REVISION B (ADNOCGP-WTRAN-xxxx)